## Action Items
ACTION ITEMS TRACKER
Capture, assign and close out actions · enter details in blue · days-to-due, overdue flags and dashboard update automatically · Eng · IT · Healthcare · Construction
ID | Action Description | Source | Owner | Priority | Status | Date Raised | Due Date | Date Done | % Complete | Days to Due | Notes
ACT-001 | [Confirm resource plan with line managers] | Meeting | [Owner A] | High | In Progress | 2026-06-20 | 2026-07-03 |  | 60% | -7 | [Two of three confirmed]
ACT-002 | [Obtain written confirmation from external provider] | Risk | [Owner B] | Critical | Not Started | 2026-06-22 | 2026-07-01 |  | 0% | -9 | [Chasing provider]
ACT-003 | [Update requirements document and circulate] | Review | [Owner C] | Medium | Complete | 2026-06-12 | 2026-06-24 | 2026-06-23 | 100% |  | [Approved and circulated]
ACT-004 | [Complete root-cause analysis of budget variance] | Issue | [Owner A] | Critical | In Progress | 2026-06-21 | 2026-07-02 |  | 40% | -8 | [Analysis under way]
ACT-005 | [Scope and schedule rework for quality defect] | Issue | [Owner D] | High | Blocked | 2026-06-23 | 2026-07-04 |  | 20% | -6 | [Awaiting parts / access]
ACT-006 | [Prepare recovery plan with vendor] | Meeting | [Owner B] | Medium | Not Started | 2026-06-24 | 2026-07-14 |  | 0% | 4 | [Meeting scheduled]
ACT-007 | [Close out safety corrective action] | Issue | [Owner E] | Critical | Complete | 2026-06-10 | 2026-06-18 | 2026-06-17 | 100% |  | [Verified and closed]
ACT-008 | [Validate integration fix in test environment] | Issue | [Owner C] | High | In Progress | 2026-06-25 | 2026-07-09 |  | 50% | -1 | [In test]
ACT-009 | [Document decision and update register] | Decision | [Owner A] | Low | Complete | 2026-06-09 | 2026-06-20 | 2026-06-19 | 100% |  | [Recorded]
ACT-010 | [Run impact assessment for change request] | Review | [Owner D] | Medium | Not Started | 2026-06-26 | 2026-07-16 |  | 0% | 6 | [Scheduled]
ACT-011 | [Re-estimate cost with latest data] | Issue | [Owner A] | Medium | In Progress | 2026-06-28 | 2026-07-13 |  | 30% | 3 | [Gathering actuals]
ACT-012 | [Coordinate access / change window] | Meeting | [Owner C] | Medium | In Progress | 2026-06-27 | 2026-07-04 |  | 70% | -6 | [Window being agreed]
ACT-013 | [Follow up third-party approval] | Risk | [Owner B] | Critical | Blocked | 2026-06-30 | 2026-07-03 |  | 10% | -7 | [Escalated]
ACT-014 | [Prepare status pack for steering review] | Meeting | [Owner E] | High | Not Started | 2026-07-01 | 2026-07-08 |  | 0% | -2 | [Template ready]
ACT-015 | [Refresh risk register after review] | Review | [Owner A] | Low | In Progress | 2026-06-29 | 2026-07-10 |  | 40% | 0 | [In progress]
Formulas:
Days to Due = IF([Status]="Complete","",IF([Due Date]="","",[Due Date]-TODAY()))

## Dashboard
ACTION ITEMS — DASHBOARD
Live summary of status, ownership, priority and completion · updates automatically from the tracker
TOTAL ACTIONS | OPEN | OVERDUE | BLOCKED | COMPLETE | % COMPLETE
15 | 12 | 8 | 2 | 3 | 41.33%
STATUS, OWNER, PRIORITY & COMPLETION
[6 empty] | Not Started | 4 | Owner A | 5 | Critical | 4 | Not Started | 4 | Done | 41.33%
[6 empty] | In Progress | 6 | Owner B | 3 | High | 4 | In Progress | 6 | Rest | 0.58667
[6 empty] | Blocked | 2 | Owner C | 3 | Medium | 5 | Blocked | 2
[6 empty] | Complete | 3 | Owner D | 2 | Low | 2 | Complete | 3
[8 empty] | Owner E | 2