## Assumption Log
ASSUMPTION & CONSTRAINT LOG
Record assumptions and constraints, their confidence and impact, and validate them · enter details in blue · flags and dashboard update automatically · Eng · IT · Healthcare · Construction
ID | Type | Description | Category | Confidence | Impact if Invalid | Status | Owner | Date Raised | Review By | Validation Action / Notes
ASM-001 | Assumption | [Required resources will be available as planned] | Resource | Medium | High | Open | [Owner A] | 2026-06-15 | 2026-07-06 | [Confirm resource plan with line managers]
ASM-002 | Assumption | [Third-party interfaces will be ready on schedule] | External | Low | High | Open | [Owner B] | 2026-06-16 | 2026-07-03 | [Obtain written confirmation from provider]
ASM-003 | Constraint | [Fixed budget ceiling for the project] | Cost | High | High | Validated | [Owner C] | 2026-06-10 | 2026-06-20 | [Confirmed in approved business case]
ASM-004 | Constraint | [Mandatory completion before a fixed deadline] | Schedule | High | High | Validated | [Owner A] | 2026-06-11 | 2026-06-22 | [Deadline confirmed by sponsor]
ASM-005 | Assumption | [Existing infrastructure can support the solution] | Technical | Medium | Medium | Open | [Owner D] | 2026-06-18 | 2026-07-10 | [Technical assessment scheduled]
ASM-006 | Assumption | [Regulatory approvals will be granted in time] | Regulatory | Low | High | Open | [Owner E] | 2026-06-20 | 2026-07-01 | [Track approval status weekly]
ASM-007 | Constraint | [Work limited to approved change windows] | Technical | High | Medium | Validated | [Owner C] | 2026-06-12 | 2026-06-24 | [Change windows agreed with operations]
ASM-008 | Assumption | [Scope will remain stable through delivery] | Scope | Medium | High | Open | [Owner A] | 2026-06-22 | 2026-07-12 | [Baseline scope; manage via change control]
ASM-009 | Assumption | [Stakeholders available for reviews as needed] | Business | Medium | Medium | Validated | [Owner B] | 2026-06-14 | 2026-06-26 | [Review calendar confirmed]
ASM-010 | Constraint | [Solution must meet defined standards] | Regulatory | High | High | Validated | [Owner D] | 2026-06-13 | 2026-06-25 | [Standards confirmed and referenced]
ASM-011 | Assumption | [Vendor pricing will hold for the quotation period] | Cost | Medium | Medium | Open | [Owner C] | 2026-06-24 | 2026-07-14 | [Confirm validity period in writing]
ASM-012 | Assumption | [Data migration volumes are as estimated] | Technical | Low | Medium | Invalidated | [Owner E] | 2026-06-09 | 2026-06-19 | [Actuals higher; re-plan required]
ASM-013 | Constraint | [Limited access to the site / environment] | Technical | High | Medium | Open | [Owner A] | 2026-06-26 | 2026-07-04 | [Coordinate access schedule]
ASM-014 | Assumption | [No major weather / external disruption] | External | Medium | Low | Open | [Owner B] | 2026-06-28 | 2026-07-16 | [Monitor; hold schedule contingency]

## Dashboard
ASSUMPTION & CONSTRAINT LOG — DASHBOARD
Live summary of status, impact, type and category · updates automatically from the log
TOTAL ITEMS | OPEN | VALIDATED | HIGH IMPACT | INVALIDATED | % VALIDATED
14 | 8 | 5 | 7 | 1 | 35.71%
STATUS, IMPACT, TYPE & CATEGORY
[6 empty] | Open | 8 | High | 7 | Technical | 4 | Assumption | 9 | Open | 8 | Assumption | 9
[6 empty] | Validated | 5 | Medium | 6 | Resource | 1 | Constraint | 5 | Validated | 5 | Constraint | 5
[6 empty] | Invalidated | 1 | Low | 1 | Schedule | 1 |  |  | Invalidated | 1
[6 empty] | Closed | 0 |  |  | Cost | 2 |  |  | Closed | 0
[10 empty] | Scope | 1
[10 empty] | External | 2
[10 empty] | Regulatory | 2
[10 empty] | Business | 1
[10 empty] | Other | 0