## Change Log
CHANGE REQUEST LOG
Register and track change requests · enter details in blue · schedule and cost impact roll up automatically · the dashboard updates automatically · Eng · IT · Healthcare · Construction
CR ID | Change Title | Type | Requestor | Date Raised | Priority | Status | Sched Δ (d) | Cost Δ | Decided | Notes
CR-001 | [Additional deliverable added to scope] | Scope | [Owner A] | 2026-06-12 | High | Implemented | 3 | 8500 | 2026-06-18 | [Baselines updated]
CR-002 | [Schedule extension for milestone] | Schedule | [Owner B] | 2026-06-15 | Medium | Approved | 5 | 0 | 2026-06-22 | [Awaiting implementation]
CR-003 | [Cost reduction proposal] | Cost | [Owner C] | 2026-06-18 | Medium | Under Review | 0 | -4000 |  | [CCB review pending]
CR-004 | [Rework to meet quality standard] | Quality | [Owner D] | 2026-06-20 | High | Approved | 2 | 3200 | 2026-06-26 | [Scheduled]
CR-005 | [Add resource to recover schedule] | Resource | [Owner E] | 2026-06-22 | Critical | Under Review | -2 | 12000 |  | [Escalated to sponsor]
CR-006 | [Technical redesign of component] | Technical | [Owner A] | 2026-06-24 | High | Submitted | 4 | 6500 |  | [Impact assessment]
CR-007 | [Reduce scope of optional feature] | Scope | [Owner B] | 2026-06-25 | Low | Approved | -3 | -2500 | 2026-06-30 | [Descoped]
CR-008 | [Change of supplier / vendor] | Other | [Owner C] | 2026-06-26 | Medium | Deferred | 1 | 1500 | 2026-06-30 | [Revisit next phase]
CR-009 | [Safety enhancement to design] | Quality | [Owner D] | 2026-06-28 | Critical | Approved | 1 | 4200 | 2026-07-02 | [Priority]
CR-010 | [Compress schedule via overlap] | Schedule | [Owner E] | 2026-06-29 | High | Under Review | -4 | 5000 |  | [Fast-track review]
CR-011 | [Approve budget increase] | Cost | [Owner A] | 2026-06-30 | High | Approved | 0 | 7800 | 2026-07-03 | [Funded]
CR-012 | [Minor specification update] | Technical | [Owner B] | 2026-07-01 | Low | Submitted | 0 | 800 |  | [Logged]
CR-013 | [Additional scope — not approved] | Scope | [Owner C] | 2026-07-01 | Medium | Rejected | 6 | 9000 | 2026-07-03 | [Out of scope]
CR-014 | [Configuration parameter change] | Other | [Owner D] | 2026-07-02 | Low | Implemented | 0 | 300 | 2026-07-03 | [Applied]

## Dashboard
CHANGE REQUESTS — DASHBOARD
Live summary of status, type, priority and impact · updates automatically from the Change Log
TOTAL CRs | OPEN | APPROVED / IMPL. | REJ. / DEFERRED | APPROVED COST Δ | APPROVED SCHED Δ
14 | 5 | 7 | 2 | 21500 | 8
STATUS, TYPE, PRIORITY & COST IMPACT
[6 empty] | Submitted | 2 | Scope | 3 | Critical | 2 | Scope | 15000 | Submitted | 2 | Critical | 2
[6 empty] | Under Review | 3 | Schedule | 2 | High | 5 | Schedule | 5000 | Under Review | 3 | High | 5
[6 empty] | Approved | 5 | Cost | 2 | Medium | 4 | Cost | 3800 | Approved | 5 | Medium | 4
[6 empty] | Rejected | 1 | Quality | 2 | Low | 3 | Quality | 7400 | Rejected | 1 | Low | 3
[6 empty] | Deferred | 1 | Resource | 1 |  |  | Resource | 12000 | Deferred | 1
[6 empty] | Implemented | 2 | Technical | 2 |  |  | Technical | 7300 | Implemented | 2
[8 empty] | Other | 2 |  |  | Other | 1800