## Issue Log
ISSUE LOG
Track, prioritise and resolve project issues · enter details in blue · age, overdue flags and dashboard update automatically · Eng · IT · Healthcare · Construction
ID | Issue Description | Category | Priority | Status | Owner | Date Raised | Target Date | Date Resolved | Age (days) | Resolution / Notes
ISS-001 | [Key deliverable at risk of slipping due to dependency delay] | Schedule | High | In Progress | [Owner A] | 2026-06-16 | 2026-07-02 |  | 24 | [Mitigation in progress; tracking dependency]
ISS-002 | [Resource shortfall in specialist skill area] | Resource | High | Open | [Owner B] | 2026-06-18 | 2026-07-08 |  | 22 | [Recruiting / reallocating; escalated]
ISS-003 | [Requirement ambiguity needs clarification] | Scope | Medium | Resolved | [Owner C] | 2026-06-12 | 2026-06-25 | 2026-06-24 | 12 | [Clarified with stakeholders; documented]
ISS-004 | [Budget variance flagged on a work package] | Cost | Critical | Open | [Owner A] | 2026-06-20 | 2026-07-01 |  | 20 | [Root-cause analysis under way]
ISS-005 | [Quality defect found during inspection/testing] | Quality | High | In Progress | [Owner D] | 2026-06-22 | 2026-07-10 |  | 18 | [Rework scoped; retest scheduled]
ISS-006 | [External vendor deliverable delayed] | External | Medium | Open | [Owner B] | 2026-06-24 | 2026-07-14 |  | 16 | [Vendor engaged; recovery plan requested]
ISS-007 | [Safety observation requires corrective action] | Safety | Critical | Resolved | [Owner E] | 2026-06-10 | 2026-06-18 | 2026-06-17 | 7 | [Corrective action closed; verified]
ISS-008 | [Integration/interface issue between systems] | Technical | High | In Progress | [Owner C] | 2026-06-25 | 2026-07-09 |  | 15 | [Fix in test; awaiting validation]
ISS-009 | [Stakeholder concern raised at review] | Stakeholder | Medium | Closed | [Owner A] | 2026-06-09 | 2026-06-20 | 2026-06-19 | 10 | [Addressed; stakeholder satisfied]
ISS-010 | [Scope change request pending assessment] | Scope | Low | Open | [Owner D] | 2026-06-26 | 2026-07-16 |  | 14 | [Impact assessment scheduled]
ISS-011 | [Documentation gap identified] | Quality | Low | Resolved | [Owner B] | 2026-06-14 | 2026-06-28 | 2026-06-27 | 13 | [Documents updated and approved]
ISS-012 | [Access / environment availability constraint] | Technical | Medium | Open | [Owner C] | 2026-06-27 | 2026-07-11 |  | 13 | [Coordinating access window]
ISS-013 | [Cost estimate needs revalidation] | Cost | Medium | In Progress | [Owner A] | 2026-06-28 | 2026-07-13 |  | 12 | [Re-estimating with latest data]
ISS-014 | [Schedule conflict across parallel activities] | Schedule | High | Open | [Owner E] | 2026-06-30 | 2026-07-04 |  | 10 | [Re-sequencing under review]
ISS-015 | [Third-party approval outstanding] | External | Critical | Open | [Owner B] | 2026-07-01 | 2026-07-07 |  | 9 | [Escalated; follow-up daily]
Formulas:
Age (days) = IF([Date Raised]="","",IF([Date Resolved]<>"",[Date Resolved]-[Date Raised],TODAY()-[Date Raised]))

## Dashboard
ISSUE LOG — DASHBOARD
Live summary of issue status, priority and category · updates automatically from the Issue Log
TOTAL ISSUES | OPEN | OVERDUE | CRITICAL / HIGH | AVG AGE (days) | % RESOLVED
15 | 11 | 6 | 8 | 14 | 26.67%
ISSUES BY STATUS, PRIORITY & CATEGORY
[6 empty] | Open | 7 | Critical | 3 | Technical | 2 | Open | 7 | Done | 0.26667
[6 empty] | In Progress | 4 | High | 5 | Resource | 1 | In Progress | 4 | Rest | 0.73333
[6 empty] | Resolved | 3 | Medium | 5 | Schedule | 2 | Resolved | 3
[6 empty] | Closed | 1 | Low | 2 | Cost | 2 | Closed | 1
[10 empty] | Quality | 2
[10 empty] | Scope | 2
[10 empty] | External | 2
[10 empty] | Safety | 1
[10 empty] | Stakeholder | 1
[10 empty] | Other | 0