## Lessons Register
LESSONS LEARNED REGISTER
Capture what worked and what to improve, with recommendations to carry forward · enter details in blue · the dashboard updates automatically · Eng · IT · Healthcare · Construction
ID | Lesson | Category | Phase | Type | Impact | Root Cause / Context | Recommendation | Owner | Status
LL-01 | [Early stakeholder engagement paid off] | Stakeholder | Initiation | Positive | High | [Workshops held up front] | [Repeat early engagement on future projects] | [Owner A] | Closed
LL-02 | [Requirements churn caused rework] | Requirements | Planning | Negative | High | [Requirements not fully baselined] | [Freeze scope earlier; stronger change control] | [Owner B] | Actioned
LL-03 | [Reusable design components saved time] | Design | Execution | Positive | Medium | [Component library reused] | [Invest in a shared component library] | [Owner C] | Closed
LL-04 | [Vendor delays affected schedule] | Procurement | Execution | Negative | High | [Single-source dependency] | [Qualify backup suppliers early] | [Owner D] | Open
LL-05 | [Daily stand-ups improved flow] | Communication | Execution | Positive | Medium | [Consistent cadence] | [Keep short daily check-ins] | [Owner A] | Closed
LL-06 | [Test environment instability] | Testing | Testing | Negative | Medium | [Environment shared & unstable] | [Provision dedicated test environment] | [Owner E] | Actioned
LL-07 | [Risk reviews prevented surprises] | Risk | Planning | Positive | High | [Regular risk workshops] | [Maintain a live risk cadence] | [Owner B] | Closed
LL-08 | [Underestimated integration effort] | Planning | Planning | Negative | High | [Optimistic estimates] | [Use reference data for estimates] | [Owner C] | Actioned
LL-09 | [Strong team collaboration] | Resource | Execution | Positive | Medium | [Co-located / aligned team] | [Protect team continuity] | [Owner A] | Closed
LL-10 | [Documentation lagged delivery] | Process | Execution | Negative | Medium | [Docs deprioritised] | [Treat docs as a deliverable per sprint] | [Owner D] | Open
LL-11 | [Automated checks caught defects] | Quality | Testing | Positive | High | [Automation in pipeline] | [Expand automated testing] | [Owner E] | Closed
LL-12 | [Unclear roles early on] | Resource | Initiation | Negative | Low | [RACI defined late] | [Agree RACI at kickoff] | [Owner B] | Actioned
LL-13 | [Phased delivery reduced risk] | Execution | Execution | Positive | Medium | [Incremental releases] | [Prefer incremental delivery] | [Owner C] | Closed
LL-14 | [Change requests poorly triaged] | Process | Execution | Negative | Medium | [No triage cadence] | [Weekly change triage] | [Owner D] | Open
LL-15 | [Clear acceptance criteria helped] | Quality | Closure | Positive | High | [Criteria agreed up front] | [Define acceptance criteria early] | [Owner A] | Closed
LL-16 | [Handover rushed at the end] | Process | Closure | Negative | Medium | [Transition planned late] | [Plan transition-out from the start] | [Owner E] | Open

## Dashboard
LESSONS LEARNED — DASHBOARD
Live summary by type, category, phase and impact · updates automatically from the register
TOTAL LESSONS | POSITIVE | NEGATIVE | HIGH IMPACT | ACTIONED / CLOSED | OPEN
16 | 8 | 8 | 7 | 12 | 4
TYPE, IMPACT, CATEGORY & PHASE
[6 empty] | Positive | 8 | High | 7 | Planning | 1 | Initiation | 2 | Positive | 8 | High | 7
[6 empty] | Negative | 8 | Medium | 8 | Requirements | 1 | Planning | 3 | Negative | 8 | Medium | 8
[8 empty] | Low | 1 | Design | 1 | Execution | 7 |  |  | Low | 1
[10 empty] | Execution | 1 | Testing | 2
[10 empty] | Testing | 1 | Closure | 2
[10 empty] | Communication | 1
[10 empty] | Stakeholder | 1
[10 empty] | Risk | 1
[10 empty] | Procurement | 1
[10 empty] | Resource | 2
[10 empty] | Quality | 2
[10 empty] | Process | 3