## Milestone List
MILESTONE LIST
Key milestones with baseline vs. forecast dates and automatic slippage · Engineering · IT · Healthcare · Construction
MILESTONES |  | ACHIEVED |  | UPCOMING |  | AT RISK / MISSED
4 |  | 1 |  | 3 |  | 0
# | Milestone | Description | Baseline Date | Forecast / Actual | Owner | Status | Variance (days) | Milestone | Days from first
1 | Project kick-off | Project formally started | 2026-01-15 | 2026-01-15 | [Owner] | Achieved | 0 | Project kick-off | 0
2 | Design / requirements sign-off | Baseline of scope and design | 2026-03-02 | 2026-03-06 | [Owner] | On Track | 4 | Design / requirements sign-off | 50
3 | Build / execution complete | All deliverables built | 2026-06-01 | 2026-06-01 | [Owner] | Not Started | 0 | Build / execution complete | 137
4 | Go-live / handover | Solution deployed and accepted | 2026-07-15 | 2026-07-15 | [Owner] | Not Started | 0 | Go-live / handover | 181
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A