## Roadmap
PROJECT ROADMAP
Visual timeline of initiatives by workstream across the year · bars fill automatically from Start / End dates and colour by status · enter details in blue · Eng · IT · Healthcare · Construction
ID | Initiative | Workstream | Start | End | Status | Prog | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
R-01 | [Platform setup] | Foundation | 2026-01-01 | 2026-03-31 | Done | 100%
R-02 | [Security baseline] | Foundation | 2026-02-01 | 2026-04-30 | Done | 100%
R-03 | [Environment automation] | Foundation | 2026-03-01 | 2026-05-31 | In Progress | 70%
R-04 | [Core product MVP] | Product | 2026-02-01 | 2026-06-30 | In Progress | 60%
R-05 | [User onboarding] | Product | 2026-05-01 | 2026-07-31 | In Progress | 40%
R-06 | [Mobile app] | Product | 2026-07-01 | 2026-10-31 | Planned | 0%
R-07 | [Data pipeline] | Data & Analytics | 2026-04-01 | 2026-06-30 | In Progress | 55%
R-08 | [Reporting & dashboards] | Data & Analytics | 2026-06-01 | 2026-08-31 | Planned | 0%
R-09 | [Predictive analytics] | Data & Analytics | 2026-09-01 | 2026-12-31 | Planned | 0%
R-10 | [Support model] | Operations | 2026-05-01 | 2026-07-31 | At Risk | 30%
R-11 | [Monitoring & SRE] | Operations | 2026-07-01 | 2026-09-30 | Planned | 0%
R-12 | [Scale & optimisation] | Operations | 2026-10-01 | 2026-12-31 | Planned | 0%
KEY MILESTONES ◆ | [8 empty] | ◆ |  |  | ◆ |  |  |  | ◆ |  | ◆
◆ Mar: Platform live · Jun: MVP launch · Oct: Mobile launch · Dec: Full scale
Legend: ■ Done ■ In Progress ■ At Risk ■ Planned · bars fill from Start/End dates

## Dashboard
ROADMAP — DASHBOARD
Initiatives by status and workstream, and overall progress · updates automatically from the roadmap
INITIATIVES | DONE | IN PROGRESS | AT RISK | PLANNED | OVERALL PROGRESS
12 | 2 | 4 | 1 | 5 | 37.92%
STATUS, WORKSTREAM & PROGRESS
[6 empty] | Planned | 5 | Foundation | 3 | Foundation | 0.9 | Planned | 5 | Value | 0.37917
[6 empty] | In Progress | 4 | Product | 3 | Product | 0.33333 | In Progress | 4 | Rest | 0.62083
[6 empty] | At Risk | 1 | Data & Analytics | 3 | Data & Analytics | 0.18333 | At Risk | 1
[6 empty] | Done | 2 | Operations | 3 | Operations | 0.1 | Done | 2