## Slide 1
Project Summary
Engineering & Construction Projects
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
Safety
Hazard & Operability (HAZOP) study completed
Zero lost-time incidents; near misses reviewed
Schedule
Pre-commissioning starts [date]
Commissioning starts [date]
Quality
Inspection & test plan completed
Material qualification in progress
Budget
Budget [amount], incl. contingency
Spent to date [amount]
Risk
No major risks identified
Tracked through weekly reviews
Key Achievements This Period
Design phase completed; final installation underway
Issued-for-Construction package, heat tracing, insulation and piping materials approved and ordered
Equipment skid datasheets approved and ordered
Equipment relocation completed (skids, piping, electrical, racks)
Automation input/output cards procured and issued
Long-lead electrical equipment allocated
External piping hydrotest completed; piping and cabling completed
Next Milestones & Plan
Piping hydrotest in remaining areas by [date]
Remaining control valves installed by [date]
Factory Acceptance Tests: [status by package]
Equipment delivery: [status]
Materials delivery: [status]

## Slide 2
Overall Status
Project health at a glance — Red, Amber, Green
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
Scope
On Track
[Brief comment]
Schedule
On Track
[Brief comment]
Cost / Budget
On Track
[Brief comment]
Health, Safety & Environment
On Track
[Brief comment]
Quality
On Track
[Brief comment]
Risk
On Track
[Brief comment]
Executive Summary
[In two or three sentences, summarize progress this period, the overall health of the project, and any items that need management attention. Replace each status above with On Track (green), At Risk (amber), or Off Track (red).]

## Slide 3
Schedule & Milestones
Key milestones with baseline, forecast, progress and status
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
Milestone | Baseline Date | Forecast / Actual | % Complete | Status
Design complete | [Date] | [Date] | [%] | On Track
Procurement complete | [Date] | [Date] | [%] | On Track
Construction complete | [Date] | [Date] | [%] | On Track
Commissioning complete | [Date] | [Date] | [%] | At Risk
Handover & closeout | [Date] | [Date] | [%] | On Track
[Tip: keep this list to the milestones that define the project. The detailed schedule (Gantt chart) is maintained separately.]

## Slide 4
Cost & Budget
Approved budget versus commitments and actual spend
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
[Amount]
Approved Budget
[Amount]
Committed to Date
[Amount]
Actual Spend to Date
[Amount]
Forecast at Completion
Item | Amount | Notes
Approved Budget | [Amount] | [Including contingency]
Contingency | [Amount] | [Percentage of budget]
Committed to Date | [Amount] | [Purchase orders and contracts placed]
Actual Spend to Date | [Amount] | [Invoiced and paid]
Variance to Budget | [Amount / %] | [Favourable or adverse]

## Slide 5
Risks, Issues & Changes
Key risks and issues, and change orders this period
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
Risks & Issues
No. | Risk / Issue | Impact | Mitigation / Action | Owner
1 | [Describe the risk or issue] | [H/M/L] | [Action in progress] | [Name]
2 |  |  |  | 
3 |  |  |  | 
Change Orders & Variations
No. | Description | Cost Impact | Schedule Impact | Status
1 | [Describe the change] | [Amount] | [Days] | Pending
2 |  |  |  | 
3 |  |  |  | 

## Slide 6
Action Log
Open and recently closed actions
Project: [Name] Report No. [ ] Period: [From – To]
Weekly Project Status Report
Date Raised | Area | Action | Owner | Status
[Date] | [Area] | [Describe the action] | [Name] | To Do
[Date] | [Area] | [Describe the action] | [Name] | Ongoing
[Date] | [Area] | [Describe the action] | [Name] | Done