## Punch List
PUNCH LIST
A printable list of outstanding items · tick each one off as it is completed and signed off · the totals at the foot update as you go
Project | [Project or property name] |  |  | Inspected | 2026-07-17
Item | Room or Area | What Needs Putting Right | Trade | Priority | Target Date | Done | Signed Off By
1 | [Kitchen] | [Cupboard door not aligned] | Joinery | Medium | 2026-07-31 | Yes | [Client] | Joinery | 8 | Done | 18 | Value | 0.6
2 | [Kitchen] | [Silicone bead untidy at worktop join] | Tiling | Low | 2026-07-31 | Yes | [Client] | Plumbing | 6 | Outstanding | 12 | Rest | 0.4
3 | [Kitchen] | [Socket faceplate marked] | Electrical | Low | 2026-07-31 | Yes | [Client] | Electrical | 6
4 | [Kitchen] | [Extract fan noisy on boost setting] | Mechanical | Medium | 2026-07-31 | No |  | Tiling | 3
5 | [Kitchen] | [Tile grout colour inconsistent by window] | Tiling | Medium | 2026-07-31 | No |  | Decoration | 3
6 | [Bathroom] | [Shower door catches on the frame] | Plumbing | High | 2026-07-31 | Yes | [Client] | Flooring | 2
7 | [Bathroom] | [Basin waste slow to drain] | Plumbing | High | 2026-07-31 | No |  | Plastering | 1
8 | [Bathroom] | [Towel rail not level] | Plumbing | Low | 2026-07-31 | Yes | [Client] | Mechanical | 1
9 | [Bathroom] | [Sealant missing behind the bath] | Tiling | High | 2026-07-31 | No
10 | [Bathroom] | [Extract fan not running on the light switch] | Electrical | Medium | 2026-07-31 | Yes | [Client]
11 | [Hallway] | [Paint finish patchy above the skirting] | Decoration | Low | 2026-07-31 | Yes | [Client]
12 | [Hallway] | [Floor covering lifting at the threshold] | Flooring | Medium | 2026-07-31 | No
13 | [Hallway] | [Light switch not aligned with the others] | Electrical | Low | 2026-07-31 | Yes | [Client]
14 | [Living room] | [Radiator valve dripping] | Plumbing | High | 2026-07-31 | No
15 | [Living room] | [Skirting board gap at the corner] | Joinery | Low | 2026-07-31 | Yes | [Client]
16 | [Living room] | [Ceiling rose not centred] | Electrical | Low | 2026-07-31 | Yes | [Client]
17 | [Living room] | [Window handle stiff] | Joinery | Medium | 2026-07-31 | No
18 | [Bedroom 1] | [Door does not close fully] | Joinery | Medium | 2026-07-31 | Yes | [Client]
19 | [Bedroom 1] | [Paint splashes on the window board] | Decoration | Low | 2026-07-31 | Yes | [Client]
20 | [Bedroom 1] | [Wardrobe shelf not secure] | Joinery | Medium | 2026-07-31 | No
21 | [Bedroom 2] | [Plaster crack above the door] | Plastering | Medium | 2026-07-31 | No
22 | [Bedroom 2] | [Carpet gripper visible at the edge] | Flooring | Low | 2026-07-31 | Yes | [Client]
23 | [Bedroom 2] | [Socket loose in the wall] | Electrical | High | 2026-07-31 | No
24 | [Landing] | [Handrail bracket loose] | Joinery | High | 2026-07-31 | Yes | [Client]
25 | [Landing] | [Loft hatch does not sit flush] | Joinery | Medium | 2026-07-31 | No
26 | [Landing] | [Smoke alarm not fixed to the ceiling] | Electrical | High | 2026-07-31 | Yes | [Client]
27 | [External] | [Render chipped beside the back door] | Decoration | Medium | 2026-07-31 | No
28 | [External] | [Outside tap drips] | Plumbing | Medium | 2026-07-31 | Yes | [Client]
29 | [External] | [Downpipe not clipped to the wall] | Plumbing | Medium | 2026-07-31 | Yes | [Client]
30 | [External] | [Gate does not latch] | Joinery | Low | 2026-07-31 | Yes | [Client]
ITEMS · DONE · OUTSTANDING · COMPLETE |  |  |  | 30 | 18 | 12 | 60%
A high-priority item still outstanding shades its whole row, so the ones that matter stand out on a printed sheet as well as on screen. Sign each item off as it is accepted — an item marked done but not signed is only half closed.