## Dashboard
RACI Matrix — Dashboard
Responsibility coverage and role workload — for engineering, IT, healthcare, and construction
PROJECT INFORMATION
Project Name | [Project name] |  |  |  | Project Manager |  | [Name]
Project Number | [Number] |  |  |  | Prepared By |  | [Name]
Client / Owner | [Organization] |  |  |  | Date |  | [DD-Mmm-YY]
COVERAGE
29 |  | 10 |  |  | 29 |  |  | 0
Activities |  | Project Roles |  |  | Valid Assignments |  |  | Need Attention
ROLE WORKLOAD ANALYSIS
Role |  |  |  | R | A | C | I | Total
Project Sponsor |  |  |  | 0 | 5 | 1 | 13 | 19
Project Manager |  |  |  | 4 | 13 | 2 | 10 | 29
Business Analyst |  |  |  | 7 | 0 | 6 | 0 | 13
Design Lead |  |  |  | 1 | 3 | 12 | 3 | 19
Procurement Lead |  |  |  | 4 | 0 | 5 | 0 | 9
Technical Lead |  |  |  | 8 | 2 | 10 | 5 | 25
Implementation Lead |  |  |  | 2 | 2 | 6 | 0 | 10
Quality Lead |  |  |  | 1 | 3 | 8 | 3 | 15
Change & Training Lead |  |  |  | 1 | 1 | 2 | 0 | 4
Operations & End Users |  |  |  | 1 | 0 | 6 | 1 | 8
Tip: a role with many A's may be an accountability bottleneck; a role with very high totals may be over-allocated.
WORKLOAD BY PHASE (involvements per role in each stage)
Role |  | Initiation | Req. & Design | Procurement | Build | Testing | Handover | Total
Project Sponsor |  | 6 | 3 | 4 | 1 | 1 | 4 | 19
Project Manager |  | 6 | 5 | 4 | 5 | 4 | 5 | 29
Business Analyst |  | 5 | 4 | 0 | 1 | 2 | 1 | 13
Design Lead |  | 5 | 5 | 2 | 4 | 0 | 3 | 19
Procurement Lead |  | 3 | 0 | 4 | 1 | 0 | 1 | 9
Technical Lead |  | 5 | 4 | 4 | 5 | 3 | 4 | 25
Implementation Lead |  | 2 | 0 | 1 | 4 | 1 | 2 | 10
Quality Lead |  | 2 | 3 | 1 | 3 | 4 | 2 | 15
Change & Training Lead |  | 0 | 0 | 0 | 2 | 0 | 2 | 4
Operations & End Users |  | 2 | 1 | 0 | 0 | 1 | 4 | 8
Darker cells show where a role is busiest. Phases: Initiation & Planning · Requirements & Design · Procurement & Resourcing · Build & Implementation · Testing & Quality Assurance · Deployment & Handover.

## RACI Matrix
RACI Matrix
Responsibility assignment for project activities — for engineering, information technology, healthcare, and construction projects
| R | Responsible |  | A | Accountable |  | C | Consulted |  | I | Informed
ACTIVITY |  | PROJECT ROLES — RESPONSIBILITY ASSIGNMENT | [9 empty] | CHECK
Code | Activity / Deliverable | Project Sponsor | Project Manager | Business Analyst | Design Lead | Procurement Lead | Technical Lead | Implementation Lead | Quality Lead | Change & Training Lead | Operations & End Users | RACI Check | Engagement Check
Phase 1 — Initiation & Planning
1.1 | Develop the project charter | A | R | C | I |  | I |  |  |  |  | Valid | OK
1.2 | Define scope and objectives | C | A | R | C |  | I |  |  |  | C | Valid | OK
1.3 | Identify stakeholders and governance | A | R | C | [6 empty] | I | Valid | OK
1.4 | Develop the project plan and schedule | I | A | R | C | C | C | C | C |  |  | Valid | OK
1.5 | Establish the budget and secure funding | A | R |  | I | C | I |  |  |  |  | Valid | OK
1.6 | Prepare the risk management plan | I | A | R | C | C | C | C | C |  |  | Valid | OK
Phase 2 — Requirements & Design
2.1 | Gather and document requirements | I | A | R | C |  | C |  |  |  | C | Valid | OK
2.2 | Develop the design and architecture | A: I; R: C; C: A; C: R |  |  | Valid | OK
2.3 | Prepare technical specifications | A: I; C: A; C: R; C: C |  |  | Valid | OK
2.4 | Conduct design review and approval | I | A | C | R |  | C |  | C |  |  | Valid | OK
2.5 | Confirm regulatory and compliance needs | I | A | R | C |  |  |  | C |  |  | Valid | OK
Phase 3 — Procurement & Resourcing
3.1 | Prepare the request for proposal and evaluate suppliers | I | A |  | C | R | C |  |  |  |  | Valid | OK
3.2 | Award contracts and purchase orders | I: A; A: C; C: R; C: I |  |  | Valid | OK
3.3 | Procure equipment, materials, and licences | I: I; A: A; C: R; C: C |  |  | Valid | OK
3.4 | Mobilize the project team | I | A |  | C | R | C | C | C |  |  | Valid | OK
Phase 4 — Build & Implementation
4.1 | Set up the environment, site, or infrastructure | A: I; C: C; C: A; C: R |  |  | Valid | OK
4.2 | Build, configure, or construct the solution |  | I |  | C |  | A | R | I |  |  | Valid | OK
4.3 | Install and configure systems and equipment | A: C; C: R; C: A; C: I |  |  | Valid | OK
4.4 | Manage progress, cost, and change | I | A | R | C | C | C | C | C | C |  | Valid | OK
4.5 | Prepare documentation and training materials | A: I; C: C; C: R; C: A |  | Valid | OK
Phase 5 — Testing & Quality Assurance
5.1 | Develop the test plan and acceptance criteria | A: I; R: C; C: R; C: A |  | Valid | OK
5.2 | Conduct functional and integration testing | A: I; C: R; C: C; C: A |  | Valid | OK
5.3 | Perform quality inspections and audits | I: I; A: A; C: C; C: R |  | Valid | OK
5.4 | Conduct user acceptance testing | A: I; R: C; C: A | R | Valid | OK
Phase 6 — Deployment & Handover
6.1 | Conduct training and readiness review | I: I; A: A; C: R | C | Valid | OK
6.2 | Deploy, commission, or go live | I: I; A: I; C: R; C: A | C | Valid | OK
6.3 | Hand over documentation and as-built records | A: I; C: A; C: R | C | Valid | OK
6.4 | Obtain final acceptance and sign-off | I: A; A: R; C: I; C: I; C: I | C | Valid | OK
6.5 | Conduct lessons learned and close the project | I | A | R | C | C | C | C | C | C |  | Valid | OK

## Printable Matrix
RACI Matrix — Printable Summary
One-page responsibility overview. Roles are shown as initials in the grid; see the key below.
ROLE KEY
SP | Project Sponsor | TL | Technical Lead
PM | Project Manager | IL | Implementation Lead
BA | Business Analyst | QL | Quality Lead
DL | Design Lead | CT | Change & Training Lead
PL | Procurement Lead | OP | Operations & End Users
R Responsible · A Accountable · C Consulted · I Informed
ACTIVITY |  | ROLES
Code | Activity / Deliverable | SP | PM | BA | DL | PL | TL | IL | QL | CT | OP
Phase 1 — Initiation & Planning
1.1 | Develop the project charter | ROLES SP: A; ROLES PM: R; ROLES BA: C; ROLES DL: I; ROLES TL: I
1.2 | Define scope and objectives | C | A | R | C |  | I |  |  |  | C
1.3 | Identify stakeholders and governance | ROLES SP: A; ROLES PM: R; ROLES BA: C; ROLES OP: I
1.4 | Develop the project plan and schedule | I | A | R | C | C | C | C | C
1.5 | Establish the budget and secure funding | A | R |  | I | C | I
1.6 | Prepare the risk management plan | I | A | R | C | C | C | C | C
Phase 2 — Requirements & Design
2.1 | Gather and document requirements | I | A | R | C |  | C |  |  |  | C
2.2 | Develop the design and architecture | A: I; R: C; C: A; C: R
2.3 | Prepare technical specifications | A: I; C: A; C: R; C: C
2.4 | Conduct design review and approval | I | A | C | R |  | C |  | C
2.5 | Confirm regulatory and compliance needs | I | A | R | C |  |  |  | C
Phase 3 — Procurement & Resourcing
3.1 | Prepare the request for proposal and evaluate suppliers | I | A |  | C | R | C
3.2 | Award contracts and purchase orders | I: A; A: C; C: R; C: I
3.3 | Procure equipment, materials, and licences | I: I; A: A; C: R; C: C
3.4 | Mobilize the project team | I | A |  | C | R | C | C | C
Phase 4 — Build & Implementation
4.1 | Set up the environment, site, or infrastructure | A: I; C: C; C: A; C: R
4.2 | Build, configure, or construct the solution |  | I |  | C |  | A | R | I
4.3 | Install and configure systems and equipment | A: C; C: R; C: A; C: I
4.4 | Manage progress, cost, and change | I | A | R | C | C | C | C | C | C
4.5 | Prepare documentation and training materials | A: I; C: C; C: R; C: A
Phase 5 — Testing & Quality Assurance
5.1 | Develop the test plan and acceptance criteria | A: I; R: C; C: R; C: A
5.2 | Conduct functional and integration testing | A: I; C: R; C: C; C: A
5.3 | Perform quality inspections and audits | I: I; A: A; C: C; C: R
5.4 | Conduct user acceptance testing | A: I; R: C; C: A | R
Phase 6 — Deployment & Handover
6.1 | Conduct training and readiness review | I: I; A: A; C: R | C
6.2 | Deploy, commission, or go live | I: I; A: I; C: R; C: A | C
6.3 | Hand over documentation and as-built records | A: I; C: A; C: R | C
6.4 | Obtain final acceptance and sign-off | I: A; A: R; C: I; C: I; C: I | C
6.5 | Conduct lessons learned and close the project | I | A | R | C | C | C | C | C | C

## Guide & Legend
How to Use This RACI Matrix
A RACI matrix sets out who does what on a project. Each row is an activity or deliverable, and each column is a project role. In every cell you record one of four letters — R, A, C, or I — to show how that role takes part in that activity. The result is a single, clear picture of responsibility that prevents gaps and overlaps. This workbook has three sheets: the Dashboard summarizes coverage and role workload; the RACI Matrix holds the assignments; and this Guide explains the letters and the rules. Replace the bracketed placeholders with your own information — the validation and the workload counts update automatically.
What the four letters mean
Letter | Meaning
R | Responsible — the role that does the work to complete the activity. There can be more than one.
A | Accountable — the single role answerable for the activity and its outcome. There must be exactly one.
C | Consulted — a role whose opinion is sought; this is a two-way conversation before the work is done.
I | Informed — a role kept up to date on progress or the outcome; this is one-way communication.
Rules for a healthy RACI
Rule | Why it matters
Exactly one Accountable per activity | One clear owner avoids confusion over who answers for the result.
At least one Responsible per activity | Someone must actually do the work.
Keep Consulted and Informed to a minimum | Too many slows the work down; include only those who truly need it.
Every role should have a balanced load | Watch for a role with too many A's or a very high total on the Dashboard.
The Validation column on the matrix checks the first two rules for you and flags any activity that is missing an Accountable, has more than one Accountable, or is missing a Responsible. The Dashboard then totals the letters for each role so you can spot a bottleneck or an over-allocated role at a glance. Add rows for new activities and everything updates automatically.