## Timeline
RESIDENTIAL REMODEL — TIMELINE
A simple week-by-week plan for a domestic project · enter the start date and the number of working days; the finish date and the bars are worked out for you
WORK PLAN | [7 empty] | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September
# | Task | Who | Start | Days | Finish | % Done | Status | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14
1 | [Design, drawings and permits] | [Client and designer] | 2026-06-01 | 10 | 2026-06-12 | 100% | Done
2 | [Order kitchen, bathroom and long-lead items] | [Contractor] | 2026-06-08 | 5 | 2026-06-12 | 100% | Done
3 | [Site protection and set-up] | [Contractor] | 2026-06-15 | 2 | 2026-06-16 | 100% | Done
4 | [Strip out kitchen and bathroom] | [Contractor] | 2026-06-17 | 4 | 2026-06-22 | 100% | Done
5 | [Form structural opening and fit beam] | [Contractor] | 2026-06-23 | 5 | 2026-06-29 | 100% | Done
6 | [First fix plumbing] | [Plumber] | 2026-06-30 | 5 | 2026-07-06 | 100% | Done
7 | [First fix electrical] | [Electrician] | 2026-06-30 | 5 | 2026-07-06 | 100% | Done
8 | [Insulation and sound deadening] | [Contractor] | 2026-07-07 | 2 | 2026-07-08 | 100% | Done
9 | [Plasterboard and dry lining] | [Contractor] | 2026-07-09 | 4 | 2026-07-14 | 100% | Done
10 | [Plastering and skim] | [Plasterer] | 2026-07-15 | 5 | 2026-07-21 | 60% | In progress
11 | [Screed and floor levelling] | [Contractor] | 2026-07-22 | 3 | 2026-07-24 | 0% | To start
12 | [Kitchen installation] | [Kitchen fitter] | 2026-07-27 | 6 | 2026-08-03 | 0% | To start
13 | [Bathroom installation] | [Plumber] | 2026-07-27 | 6 | 2026-08-03 | 0% | To start
14 | [Wall and floor tiling] | [Tiler] | 2026-08-04 | 5 | 2026-08-10 | 0% | To start
15 | [Floor coverings] | [Flooring fitter] | 2026-08-11 | 4 | 2026-08-14 | 0% | To start
16 | [Second fix plumbing] | [Plumber] | 2026-08-17 | 3 | 2026-08-19 | 0% | To start
17 | [Second fix electrical] | [Electrician] | 2026-08-17 | 3 | 2026-08-19 | 0% | To start
18 | [Decoration] | [Decorator] | 2026-08-20 | 6 | 2026-08-27 | 0% | To start
19 | [Snagging and making good] | [Contractor] | 2026-08-28 | 3 | 2026-09-01 | 0% | To start
20 | [Final clean and handover] | [Contractor] | 2026-09-02 | 2 | 2026-09-03 | 0% | To start
PROJECT |  |  |  | 88 | 2026-09-03 | 51.14%
Finish dates skip weekends automatically, so a five-day task starting on a Thursday runs to the following Wednesday. Bars fill themselves from the start and finish dates: green for done, blue for in progress, grey for still to start. The amber column is the current week.

## Summary
TIMELINE SUMMARY
Where the project has reached and how the work is spread
TASKS | WORKING DAYS | COMPLETE | IN PROGRESS | PROGRESS | FINISH
20 | 88 | 9 | 1 | 51.14% | 2026-09-03
PROGRESS AND WORKLOAD
[6 empty] | Done | 9 | Done | 9 | Value | 0.51136
[6 empty] | In progress | 1 | In progress | 1 | Rest | 0.48864
[6 empty] | To start | 10 | To start | 10
[6 empty] | Late start | 0 | Late start | 0