## Risk Register
RISK ASSESSMENT MATRIX & RISK REGISTER
Identify, score, respond to and track project risks · inherent vs residual · Engineering · IT · Healthcare · Construction
TOTAL RISKS |  | HIGH + EXTREME |  | OPEN |  | AVG INHERENT |  |  | AVG RESIDUAL |  |  |  | RISK REDUCTION
10 |  | 9 |  | 10 |  | 13.3 |  |  | 5.4 |  |  |  | 59.4%
CHART DATA
Risk ID | Category | Risk Description | Cause / Trigger | Potential Consequence | Prob (1-5) | Impact (1-5) | Score | Level | Response Strategy | Mitigation / Response Actions | Risk Owner | Target Date | Res. Prob | Res. Impact | Res. Score | Res. Level | Status | [7 empty] | Category | Risks |  | Level | Risks
R-01 | Technical | [Key system/equipment fails to meet performance requirements] | [Immature design; unproven technology] | [Rework, re-testing, delayed go-live] | 4 | 5 | 20 | Extreme | Mitigate | [Prototype early; staged testing; design reviews with SMEs] | [Owner] |  | 2 | 4 | 8 | Medium | Open | [7 empty] | Technical | 1 |  | Extreme | 4
R-02 | Schedule | [Critical-path activity delayed by long-lead procurement] | [Single supplier; long lead times] | [Overall completion date slips] | 4 | 4 | 16 | Extreme | Mitigate | [Place orders early; qualify a second supplier; add float] | [Owner] |  | 2 | 3 | 6 | Medium | In Progress | [7 empty] | Schedule | 1 |  | High | 5
R-03 | Cost | [Material / commodity price escalation exceeds budget] | [Market volatility; inflation] | [Budget overrun; reduced scope] | 3 | 4 | 12 | High | Transfer | [Fixed-price contracts; hedging; contingency reserve] | [Owner] |  | 2 | 3 | 6 | Medium | Monitoring | [7 empty] | Cost | 1 |  | Medium | 1
R-04 | Resource | [Loss of key skilled personnel during execution] | [Attrition; competing priorities] | [Knowledge loss; slowed progress] | 3 | 4 | 12 | High | Mitigate | [Cross-training; documented procedures; retention plan] | [Owner] |  | 2 | 2 | 4 | Low | Open | [7 empty] | Resource | 1 |  | Low | 0
R-05 | Regulatory | [Regulatory approval / permit delayed] | [Incomplete submissions; agency backlog] | [Cannot proceed to next phase] | 3 | 5 | 15 | Extreme | Mitigate | [Early engagement; pre-submission reviews; track dates] | [Owner] |  | 1 | 4 | 4 | Low | In Progress | [7 empty] | Regulatory | 1
R-06 | Safety | [Safety incident during a high-risk activity] | [Hazardous work; inadequate controls] | [Injury, stop-work, liability] | 2 | 5 | 10 | High | Mitigate | [JSA/permits; training; inspections; PPE] | [Owner] |  | 1 | 4 | 4 | Low | Monitoring | [7 empty] | Safety | 1
R-07 | Quality | [Deliverable fails acceptance testing / inspection] | [Unclear requirements; process gaps] | [Rework; acceptance delay] | 3 | 3 | 9 | Medium | Mitigate | [Clear acceptance criteria; QA checkpoints; peer review] | [Owner] |  | 2 | 2 | 4 | Low | Open | [7 empty] | Quality | 1
R-08 | External | [Third-party vendor fails to deliver to contract] | [Vendor capacity; financial issues] | [Schedule and cost impact] | 3 | 4 | 12 | High | Transfer | [SLA with penalties; backup vendor; progress audits] | [Owner] |  | 2 | 3 | 6 | Medium | Open | [7 empty] | External | 1
R-09 | Stakeholder | [Scope creep from changing requirements] | [Evolving needs; weak change control] | [Budget/schedule growth] | 4 | 3 | 12 | High | Mitigate | [Formal change control; baseline sign-off; backlog] | [Owner] |  | 2 | 2 | 4 | Low | In Progress | [7 empty] | Stakeholder | 1
R-10 | Cybersecurity | [Cybersecurity breach compromises data / systems] | [Unpatched systems; phishing] | [Data loss; downtime; penalties] | 3 | 5 | 15 | Extreme | Mitigate | [Access controls; patching; monitoring; awareness] | [Owner] |  | 2 | 4 | 8 | Medium | Monitoring | [7 empty] | Cybersecurity | 1
[25 empty] | Risk ID | Inherent | Residual
[25 empty] | R-01 | 20 | 8
[25 empty] | R-02 | 16 | 6
[25 empty] | R-03 | 12 | 6
[25 empty] | R-04 | 12 | 4
[25 empty] | R-05 | 15 | 4
[25 empty] | R-06 | 10 | 4
[25 empty] | R-07 | 9 | 4
[25 empty] | R-08 | 12 | 6
[25 empty] | R-09 | 12 | 4
[25 empty] | R-10 | 15 | 8
[22 empty] | Risk | Inherent | Residual
[22 empty] | R-01 | 20 | 8
[18 empty] | Technical | 1 | Low | 0 | R-02 | 16 | 6
[18 empty] | Schedule | 1 | Medium | 1 | R-03 | 12 | 6
[18 empty] | Cost | 1 | High | 5 | R-04 | 12 | 4
[18 empty] | Resource | 1 | Extreme | 4 | R-05 | 15 | 4
[18 empty] | Regulatory | 1 |  |  | R-06 | 10 | 4
[18 empty] | Safety | 1 |  |  | R-07 | 9 | 4
[18 empty] | Quality | 1 |  |  | R-08 | 12 | 6
[18 empty] | External | 1 |  |  | R-09 | 12 | 4
[18 empty] | Stakeholder | 1 |  |  | R-10 | 15 | 8
[18 empty] | Cybersecurity | 1

## 5x5 Matrix
5 × 5 PROBABILITY / IMPACT MATRIX
Live count of risks in each cell — drawn from the Risk Register · left: inherent right: residual
INHERENT (Probability × Impact) | [6 empty] | RESIDUAL (after response)
Impact ↓ / Prob → | 1 | 2 | 3 | 4 | 5 |  | Impact ↓ / Prob → | 1 | 2 | 3 | 4 | 5
5 | 0 | 1 | 2 | 1 | 0 |  | 5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 3 | 1 | 0 |  | 4 | 2 | 2 | 0 | 0 | 0
3 | 0 | 0 | 1 | 1 | 0 |  | 3 | 0 | 3 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 3 | 0 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0
Score bands: |  |  | Low (1-4) |  |  | Medium (5-9) |  |  | High (10-14) |  |  | Extreme (15-25)
How to read: each cell shows how many risks currently sit at that probability/impact combination. Reduce a risk by moving it toward the green (lower-left) corner through your response actions.