## Gantt Chart
PROJECT GANTT CHART
Smart, colour-coded schedule with editable workstream bars, live progress and milestones over a 52-week horizon · Engineering · IT · Healthcare · Construction
TASKS / MILESTONES |  |  | AVG % COMPLETE |  | OVERDUE |  | FINISH |  | Timeline start (Mon): |  |  |  | 2026-01-05
9 |  |  | 36.11% |  | 4 |  | 2026-08-23
Legend ▸ |  | Planning | [6 empty] | Design | [6 empty] | Procurement | [6 empty] | Build | [6 empty] | Testing | [6 empty] | Deployment | [6 empty] | Support | [6 empty] | Other | [6 empty] | Milestone ■ done · lighter = remaining
ID | Task | Workstream | Owner | Start | Days | End | % | Status | January 2026 |  |  |  | Feb 2026 |  |  |  | Mar 2026 |  |  |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026 |  |  |  | Oct 2026 |  |  |  | Nov 2026 |  |  |  |  | Dec 2026
 | time axis 2026-01-05 to 2026-12-28
M1 | Project kick-off | Planning | [Owner] | 2026-01-05 | 0 | 2026-01-05 | 100% | Complete
T1 | Requirements gathering | Planning | [Owner] | 2026-01-12 | 18 | 2026-01-29 | 100% | Complete
T2 | Solution design | Design | [Owner] | 2026-02-02 | 25 | 2026-02-26 | 70% | Overdue
T3 | Procurement / sourcing | Procurement | [Owner] | 2026-02-16 | 35 | 2026-03-22 | 40% | Overdue
T4 | Build / execution | Build | [Owner] | 2026-03-23 | 70 | 2026-05-31 | 15% | Overdue
T5 | Integration & testing | Testing | [Owner] | 2026-06-01 | 35 | 2026-07-05 | 0% | Overdue
T6 | Deployment / go-live | Deployment | [Owner] | 2026-07-13 | 14 | 2026-07-26 | 0% | Not Started
M2 | Go-live milestone | Deployment | [Owner] | 2026-07-27 | 0 | 2026-07-27 | 0% | Not Started
T7 | Hypercare / support | Support | [Owner] | 2026-07-27 | 28 | 2026-08-23 | 0% | Not Started
[7 empty] | Status | Tasks
[7 empty] | Complete | 2
[7 empty] | In Progress | 0
[7 empty] | Overdue | 4
[7 empty] | Not Started | 3
[61 empty] | Not Started | 3
[61 empty] | In Progress | 0
[61 empty] | Complete | 2
[61 empty] | Overdue | 4
[63 empty] | Not Started | 3
[63 empty] | In Progress | 0
[63 empty] | Complete | 2
[63 empty] | Overdue | 4