## Retrospective
SPRINT RETROSPECTIVE
Inspect and adapt · capture what went well, what did not, ideas and appreciations, then vote · the highest-voted items become actions on the next sheet · Eng · IT · Healthcare · Construction
Sprint | [Sprint 7] | Date | 2026-07-10 | Facilitator | [Facilitator] | Participants | 8
Sprint Goal | [State the goal the sprint set out to achieve, so the discussion stays anchored to it]
WHAT WENT WELL |  | WHAT DID NOT GO WELL |  | IDEAS & IMPROVEMENTS |  | APPRECIATIONS
Item | Votes | Item | Votes | Item | Votes | Item | Votes
[Team delivered the sprint goal on time] | 6 | [Requirements changed mid-sprint] | 8 | [Freeze scope after planning] | 7 | [Thank you for covering the on-call rota] | 4
[Daily stand-ups were focused and short] | 5 | [Too much unplanned work arrived] | 7 | [Reserve capacity for unplanned work] | 6 | [Thank you for mentoring a new member] | 3
[Automated tests caught defects early] | 4 | [Environment downtime blocked testing] | 5 | [Add an environment health check to stand-up] | 5 | [Thank you for fixing the build quickly] | 2
[Collaboration across the team was strong] | 3 | [Code reviews were slow to complete] | 4 | [Set a 24-hour code review target] | 3
[Documentation was kept up to date] | 2 | [Handover between shifts was unclear] | 3 | [Introduce a written handover note] | 2
5 items | 20 | 5 items | 27 | 5 items | 23 | 3 items | 9
How to run it: set the scene · gather data on the board · vote on the items that matter most · discuss the top-voted items · agree a small number of actions and record them on the next sheet.

## Team Health & Actions
TEAM HEALTH CHECK & RETROSPECTIVE ACTIONS
Rate each dimension from 1 (poor) to 5 (excellent) · the change against the previous sprint calculates automatically · agreed actions are tracked below
TEAM HEALTH CHECK (1 = poor · 5 = excellent)
# | Dimension | Previous | Current | Change | Status | Trend | Comment
1 | [Delivering value] | 3.5 | 4 | 0.5 | Strong | Improving
2 | [Teamwork] | 4 | 4.2 | 0.2 | Strong | Improving
3 | [Communication] | 3 | 3.6 | 0.6 | Adequate | Improving
4 | [Process and tools] | 3.2 | 3.4 | 0.2 | Adequate | Improving
5 | [Quality] | 3.8 | 4 | 0.2 | Strong | Improving
6 | [Learning and growth] | 3 | 3.2 | 0.2 | Adequate | Improving
7 | [Workload balance] | 2.8 | 3 | 0.2 | Adequate | Improving
8 | [Morale] | 3.6 | 3.8 | 0.2 | Adequate | Improving
AVERAGE |  | 3.3625 | 3.65 | 0.2875
AGREED ACTIONS (arising from the retrospective)
ID | Action | Owner | Due | Priority | Status | Source Item | Expected Outcome
A-01 | [Freeze scope after planning day] | [Owner A] | 2026-07-17 | High | In Progress | [Requirements changed mid-sprint] | [Fewer mid-sprint changes]
A-02 | [Reserve 15% capacity for unplanned work] | [Owner B] | 2026-07-17 | High | Not Started | [Too much unplanned work] | [Commitments met more often]
A-03 | [Add environment health check to stand-up] | [Owner C] | 2026-07-13 | Medium | Done | [Environment downtime] | [Blockers found earlier]
A-04 | [Agree a 24-hour code review target] | [Owner D] | 2026-07-14 | Medium | Done | [Code reviews were slow] | [Shorter cycle time]
A-05 | [Create a written shift handover template] | [Owner A] | 2026-07-24 | Medium | Not Started | [Handover was unclear] | [Cleaner handovers]
A-06 | [Review the test data refresh process] | [Owner C] | 2026-07-31 | Low | In Progress | [Testing delays] | [Reliable test data]

## Dashboard
RETROSPECTIVE — DASHBOARD
Items raised, votes, team health and action progress · updates automatically from the board and action list
ITEMS RAISED | TOTAL VOTES | TEAM HEALTH | CHANGE VS LAST | ACTIONS | ACTIONS DONE
18 | 79 | 3.65 | 0.2875 | 6 | 2
ITEMS, VOTES, HEALTH & ACTIONS
[6 empty] | Went Well | 5 | Went Well | 20 | Went Well | 5 | Value | 0.73 | Not Started | 2
[6 empty] | Did Not Go Well | 5 | Did Not Go Well | 27 | Did Not Go Well | 5 | Rest | 0.27 | In Progress | 2
[6 empty] | Ideas | 5 | Ideas | 23 | Ideas | 5 |  |  | Done | 2
[6 empty] | Appreciations | 3 | Appreciations | 9 | Appreciations | 3