## Dashboard
Work Breakdown Structure — Dashboard
Structure, roll-up estimates, and cost distribution — for engineering, IT, healthcare, and construction
PROJECT INFORMATION
Project Name | [Project name] |  |  | Project Manager | [Name]
Project Number | [Number] |  |  | Prepared By | [Name]
Client / Owner | [Organization] |  |  | Date | [DD-Mmm-YY]
KEY METRICS
51 | 6 |  | 13 | 31 | 284 |  | 691000
WBS Elements | Phases |  | Deliverables | Work Packages | Total Effort (days) |  | Total Cost
COST BY PHASE |  |  |  | EFFORT BY PHASE
Initiation & Planning |  | 56000 |  | Initiation & Planning |  | 32
Requirements & Design |  | 95000 |  | Requirements & Design |  | 50
Procurement & Resourcing |  | 125000 |  | Procurement & Resourcing |  | 36
Build & Implementation |  | 297000 |  | Build & Implementation |  | 96
Testing & Quality Assurance |  | 71000 |  | Testing & Quality Assurance |  | 44
Deployment & Handover |  | 47000 |  | Deployment & Handover |  | 26

## WBS
Work Breakdown Structure
Scope decomposition, work-package dictionary, and roll-up estimates — for engineering, information technology, healthcare, and construction projects
STRUCTURE |  |  |  |  | ESTIMATES (ROLL-UP) |  |  |  |  | WORK-PACKAGE DICTIONARY
WBS Code | WBS Element / Deliverable | Level | Type | Responsible | Effort (days) | Total Effort | Cost (Estimate) | Total Cost | % of Total Cost | Description & Scope | Acceptance Criteria | Status | Notes
1 | [Project Name] | 1 | Project | Project Manager |  | 284 |  | 691000 | 100% | The total scope of the project, decomposed into phases, deliverables, and work packages. | All deliverables completed, verified, and accepted; project formally closed. | In Progress
1.1 | Initiation & Planning | 2 | Phase | Project Manager |  | 32 |  | 56000 | 8.104% | Define the project, confirm the business case, and produce the baseline plan. | Approved charter, scope, plan, and budget. | Complete
1.1.1 | Project Definition | 3 | Deliverable | Project Manager |  | 15 |  | 27000 | 3.907% | The agreed definition of why the project exists and what it will deliver. | Charter, scope, and stakeholder register approved. | Complete
1.1.1.1 | Develop project charter | 4 | Work Package | Project Manager | 5 | 5 | 12000 | 12000 | 1.737% | Prepare and approve the project charter. | Charter signed by the sponsor. | Complete
1.1.1.2 | Define scope and objectives | 4 | Work Package | Project Manager | 6 | 6 | 9000 | 9000 | 1.302% | Document the scope, objectives, and success criteria. | Scope and objectives agreed. | Complete
1.1.1.3 | Identify stakeholders and governance | 4 | Work Package | Project Manager | 4 | 4 | 6000 | 6000 | 0.8683% | Identify stakeholders and set the governance structure. | Stakeholder register and governance approved. | Complete
1.1.2 | Project Planning | 3 | Deliverable | Project Manager |  | 17 |  | 29000 | 4.197% | The baseline plan, budget, and risk approach. | Plan, budget, and risk register approved. | Complete
1.1.2.1 | Develop project plan and schedule | 4 | Work Package | Project Manager | 8 | 8 | 14000 | 14000 | 2.026% | Develop the baseline plan and schedule. | Baseline schedule approved. | Complete
1.1.2.2 | Establish budget and secure funding | 4 | Work Package | Project Sponsor | 4 | 4 | 8000 | 8000 | 1.158% | Establish the budget and obtain funding approval. | Funding approved. | Complete
1.1.2.3 | Prepare risk management plan | 4 | Work Package | Project Manager | 5 | 5 | 7000 | 7000 | 1.013% | Identify risks and define mitigations. | Risk register approved. | Complete
1.2 | Requirements & Design | 2 | Phase | Design Lead |  | 50 |  | 95000 | 13.75% | Define the requirements and develop the design or architecture. | Approved requirements and frozen design baseline. | In Progress
1.2.1 | Requirements | 3 | Deliverable | Business Analyst |  | 18 |  | 27000 | 3.907% | The documented and agreed requirements. | Requirements baselined and signed off. | In Progress
1.2.1.1 | Gather and document requirements | 4 | Work Package | Business Analyst | 12 | 12 | 18000 | 18000 | 2.605% | Gather and document the detailed requirements. | Requirements documented. | Complete
1.2.1.2 | Review and baseline requirements | 4 | Work Package | Business Analyst | 6 | 6 | 9000 | 9000 | 1.302% | Review, agree, and baseline the requirements. | Requirements signed off. | In Progress
1.2.2 | Design | 3 | Deliverable | Design Lead |  | 32 |  | 68000 | 9.841% | The concept and detailed design. | Design reviewed and approved. | In Progress
1.2.2.1 | Develop concept design | 4 | Work Package | Design Lead | 10 | 10 | 22000 | 22000 | 3.184% | Develop the concept or preliminary design. | Concept design approved. | In Progress
1.2.2.2 | Develop detailed design and architecture | 4 | Work Package | Design Lead | 18 | 18 | 40000 | 40000 | 5.789% | Develop the detailed design and architecture. | Detailed design completed. | Not Started
1.2.2.3 | Conduct design review and approval | 4 | Work Package | Project Manager | 4 | 4 | 6000 | 6000 | 0.8683% | Hold the design review and freeze the baseline. | Design baseline frozen. | Not Started
1.3 | Procurement & Resourcing | 2 | Phase | Procurement Lead |  | 36 |  | 125000 | 18.09% | Select suppliers, award contracts, and mobilize the resources to deliver. | Contracts awarded and resources mobilized. | Not Started
1.3.1 | Sourcing & Contracts | 3 | Deliverable | Procurement Lead |  | 15 |  | 20000 | 2.894% | The supplier selection and contracts. | Contracts and purchase orders awarded. | Not Started
1.3.1.1 | Prepare request for proposal and evaluate suppliers | 4 | Work Package | Procurement Lead | 10 | 10 | 12000 | 12000 | 1.737% | Prepare the request for proposal and evaluate suppliers. | Suppliers shortlisted. | Not Started
1.3.1.2 | Award contracts and purchase orders | 4 | Work Package | Procurement Lead | 5 | 5 | 8000 | 8000 | 1.158% | Award the contracts and purchase orders. | Contracts awarded. | Not Started
1.3.2 | Resourcing | 3 | Deliverable | Project Manager |  | 21 |  | 105000 | 15.2% | The goods, services, and team needed to deliver. | Resources procured and team mobilized. | Not Started
1.3.2.1 | Procure equipment, materials, and licences | 4 | Work Package | Procurement Lead | 15 | 15 | 90000 | 90000 | 13.02% | Procure equipment, materials, software licences, or services. | Goods and services received. | Not Started
1.3.2.2 | Mobilize project team and resources | 4 | Work Package | Project Manager | 6 | 6 | 15000 | 15000 | 2.171% | Assemble and onboard the project team. | Team mobilized. | Not Started
1.4 | Build & Implementation | 2 | Phase | Technical Lead |  | 96 |  | 297000 | 42.98% | Prepare, build, and implement the solution. | Solution built, configured, and installed. | Not Started
1.4.1 | Preparation | 3 | Deliverable | Technical Lead |  | 12 |  | 35000 | 5.065% | The environment, site, or infrastructure readiness. | Environment ready for the build. | Not Started
1.4.1.1 | Set up environment, site, or infrastructure | 4 | Work Package | Technical Lead | 12 | 12 | 35000 | 35000 | 5.065% | Prepare the environment, site, or infrastructure. | Environment ready and access arranged. | Not Started
1.4.2 | Construction / Build | 3 | Deliverable | Technical Lead |  | 66 |  | 228000 | 33% | The built, configured, or constructed solution. | Solution built to the approved design. | Not Started
1.4.2.1 | Build, configure, or construct the solution | 4 | Work Package | Technical Lead | 30 | 30 | 120000 | 120000 | 17.37% | Build, configure, or construct to the approved design. | Build complete. | Not Started
1.4.2.2 | Develop and integrate components | 4 | Work Package | Technical Lead | 20 | 20 | 60000 | 60000 | 8.683% | Develop and integrate the components. | Components integrated. | Not Started
1.4.2.3 | Install and configure systems and equipment | 4 | Work Package | Implementation Lead | 16 | 16 | 48000 | 48000 | 6.946% | Install and configure the systems and equipment. | Systems installed and configured. | Not Started
1.4.3 | Delivery Management | 3 | Deliverable | Project Manager |  | 18 |  | 34000 | 4.92% | The control of progress, cost, change, and documentation. | Delivery controlled and documented. | Not Started
1.4.3.1 | Manage progress, cost, and change | 4 | Work Package | Project Manager | 10 | 10 | 20000 | 20000 | 2.894% | Track progress and cost; manage change requests. | Status reported; changes controlled. | Not Started
1.4.3.2 | Prepare documentation and training materials | 4 | Work Package | Change & Training Lead | 8 | 8 | 14000 | 14000 | 2.026% | Prepare the documentation and training materials. | Documentation and training ready. | Not Started
1.5 | Testing & Quality Assurance | 2 | Phase | Quality Lead |  | 44 |  | 71000 | 10.27% | Verify the solution against its requirements. | All tests passed and defects cleared. | Not Started
1.5.1 | Test Preparation | 3 | Deliverable | Quality Lead |  | 6 |  | 9000 | 1.302% | The test plan and acceptance criteria. | Test plan approved. | Not Started
1.5.1.1 | Develop test plan and acceptance criteria | 4 | Work Package | Quality Lead | 6 | 6 | 9000 | 9000 | 1.302% | Develop the test plan and acceptance criteria. | Test plan approved. | Not Started
1.5.2 | Testing & Inspection | 3 | Deliverable | Test Lead |  | 38 |  | 62000 | 8.973% | The executed tests, inspections, and defect clearance. | Testing complete; defects closed. | Not Started
1.5.2.1 | Conduct functional and integration testing | 4 | Work Package | Test Lead | 14 | 14 | 24000 | 24000 | 3.473% | Run the functional and integration tests. | Functional tests passed. | Not Started
1.5.2.2 | Perform quality inspections and audits | 4 | Work Package | Quality Lead | 8 | 8 | 12000 | 12000 | 1.737% | Perform the quality inspections and audits. | Inspections passed. | Not Started
1.5.2.3 | Resolve defects and non-conformances | 4 | Work Package | Technical Lead | 10 | 10 | 16000 | 16000 | 2.315% | Log and clear the defects and non-conformances. | Defects closed. | Not Started
1.5.2.4 | Conduct user acceptance testing | 4 | Work Package | Quality Lead | 6 | 6 | 10000 | 10000 | 1.447% | Conduct user acceptance and performance testing. | Acceptance testing passed. | Not Started
1.6 | Deployment & Handover | 2 | Phase | Implementation Lead |  | 26 |  | 47000 | 6.802% | Deploy the solution and hand it over to operations. | Solution live, accepted, and closed. | Not Started
1.6.1 | Deployment | 3 | Deliverable | Implementation Lead |  | 14 |  | 28000 | 4.052% | The trained users and the live solution. | Solution deployed and live. | Not Started
1.6.1.1 | Conduct training and readiness review | 4 | Work Package | Change & Training Lead | 6 | 6 | 10000 | 10000 | 1.447% | Deliver training and confirm readiness. | Training delivered; readiness confirmed. | Not Started
1.6.1.2 | Deploy, commission, or go live | 4 | Work Package | Implementation Lead | 8 | 8 | 18000 | 18000 | 2.605% | Deploy, commission, or go live. | Solution live; preliminary acceptance obtained. | Not Started
1.6.2 | Closeout | 3 | Deliverable | Project Manager |  | 12 |  | 19000 | 2.75% | The final acceptance, documentation, and closure. | Final acceptance and closure complete. | Not Started
1.6.2.1 | Hand over documentation and as-built records | 4 | Work Package | Design Lead | 5 | 5 | 8000 | 8000 | 1.158% | Hand over the final documentation and as-built records. | Documentation handed over. | Not Started
1.6.2.2 | Obtain final acceptance and sign-off | 4 | Work Package | Project Sponsor | 3 | 3 | 5000 | 5000 | 0.7236% | Obtain final acceptance and sign-off. | Final acceptance signed. | Not Started
1.6.2.3 | Conduct lessons learned and close project | 4 | Work Package | Project Manager | 4 | 4 | 6000 | 6000 | 0.8683% | Capture lessons learned and close the project. | Lessons recorded; project closed. | Not Started

## Guide & Legend
How to Use This Work Breakdown Structure
A Work Breakdown Structure (WBS) is a hierarchical, deliverable-oriented decomposition of the total scope of a project. It breaks the project down into phases, then deliverables, then small, manageable work packages. This template gives you three sheets: the Dashboard summarizes the structure and roll-up estimates; the WBS sheet holds the hierarchy and the work-package dictionary; and this Guide explains the rules, levels, and columns. Replace the bracketed placeholders with your own information — the levels, totals, and percentages update automatically.
The 100% rule
A WBS follows the 100% rule: the work packages under a parent add up to 100 percent of that parent's scope and cost — no more, no less. Because of this, you enter effort and cost only at the work-package level, and the template rolls those values up automatically to each deliverable, each phase, and the whole project.
The four levels
Level | Meaning
1 · Project | The whole project — the single top-level element.
2 · Phase | A major stage of the project lifecycle.
3 · Deliverable | A distinct output produced within a phase.
4 · Work Package | The smallest unit of work that is estimated and assigned.
Column definitions
Column | Meaning
WBS Code | The hierarchical number, for example 1.2.3.
WBS Element / Deliverable | The name of the element, indented by level.
Level | The depth in the hierarchy (calculated automatically).
Type | Project, Phase, Deliverable, or Work Package.
Responsible | The role accountable for the element.
Effort (days) / Cost | Estimates entered at the work-package level only.
Total Effort / Total Cost | The roll-up totals (calculated automatically).
% of Total Cost | The element's share of the total project cost.
Description & Scope | What the element covers.
Acceptance Criteria | The agreed definition of done.
Status | Not Started, In Progress, Complete, or On Hold.
Tip: use the small plus and minus buttons on the left of the WBS sheet to expand or collapse each phase and deliverable. The colour of each row shows its level — navy for the project, blue for phases, light blue for deliverables, and white for work packages. Everything is fully editable; add rows for new work packages and the totals will roll up automatically.